## TimeLine
Attendee Notation | Corresponding Member's Name
A | Alamul Yaqin
B | Shania Salsabilla (Bella)
C | Calvin Christian Chandra
E | Eureka Labdawara
S | Satrio Fatturahman
No. | Task and Specifics | Attendees | Date
|  |  | 2024-11-06 | 2024-12-06 | 6/13 | 6/14 | 6/15 | 6/16 | 6/17 | 6/18 | 6/19 | 6/20 | 6/21
Project planning and scheduling
| Meeting | A, B, C, E, S | bar: Date 2024-11-06
Task and data understanding
| Translation of task | B, C | bar: Date 2024-12-06 to Date 6/13
| Data preparation and preprocessing | B, C | bar: Date 2024-12-06 to Date 6/13
| Meeting (member update) | B, C, S | bar: Date 6/14
Coding
| Training algorithm understanding & creation | B, C, S | bar: Date 6/14 to Date 6/19
| Model training & algorithm evaluation 1 | B, C, S | bar: Date 6/16
| algorithm evaluation 2 | A, B, C, E, S | bar: Date 6/18
Result Analysis
| Analysis, Graphing, and Validation | B, C | bar: Date 6/19 to Date 6/21
Presentation
| Powerpoint creation | A, B, C, E, S | bar: Date 6/19 to Date 6/21
| rehearsal | A, B, C, E, S | bar: Date 6/21
Others
| Upload finished code to github | A, B, C, E, S | bar: Date 6/21

## Try Models
Models:
Pekerja | Model (pretrained = Yes) atau weights = Model_Weights.DEFAULT |  |  | Epoch | Learning Rate | Optimizer | Criterion | [11 empty] | VGG | VGG-13 | VGG-16 | VGG-19
[8 empty] | Test (Best Model) (terhadap 1.00) |  |  |  | Waktu Training | Waktu Training (s) | Best Test Acc | Machine |  |  |  | ResNet | ResNet-18 | ResNet-34 | ResNet-50
| VGG | ResNet | GoogleNet |  |  |  |  | Accuracy | Precision | Recall | F1-Score | [7 empty] | GoogleNet | V1 | V3
Bella |  | 18 |  | 10 | 0.0001 | adam | BCEWithLogitsLoss | 0.972 | 0.9212 | 0.9616 | 0.941 | 2m 37s | 157 | 0.972 | GPU T4 x2 Kaggle | Note: Accuracy (salah simpan, beda hasil sama Best Testnya karna simpannya di last_model)
|  | 18 |  | 50 | 0.0001 | adam | BCEWithLogitsLoss | 0.976 | 0.9282 | 0.9689 | 0.9481 | 12m 52s | 772 | 0.976 | GPU T4 x2 Kaggle |  |  |  | Epochs | 25
|  | 18 |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.973 | 0.9409 | 0.9598 | 0.9502 | 6m 43s | 403 | 0.973 | GPU T4 x2 Kaggle |  |  |  | lr | 0.0001
|  | 34 |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.9745 | 0.8869 | 0.9744 | 0.9286 | 9m 1s | 541 | 0.9745 | GPU T4 x2 Kaggle
|  | 50 |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.9765 | 0.8835 | 0.9707 | 0.9251 | 16m 12s | 972 | 0.9765 | GPU T4 x2 Kaggle |  |  |  | Criterion | BCEWithLogitsLoss
|  | 101 |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.9755 | 0.9017 | 0.989 | 0.9433 | 25m 42s | 1542 | 0.9755 | GPU T4 x2 Kaggle
| 11 |  |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.9715 | 0.9239 | 0.9762 | 0.9493 | 15m 39s | 939 | 0.9715 | GPU T4 x2 Kaggle |  |  |  | Metric | time, recall, precision, accuracy, f1-score
| 13 |  |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.973 | 0.9332 | 0.9707 | 0.9516 | 21m 16s | 1276 | 0.973 | GPU T4 x2 Kaggle
| 16 |  |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.973 | 0.9178 | 0.9598 | 0.9383 | 25m 10s | 1510 | 0.973 | GPU T4 x2 Kaggle |  |  |  | Pretrained?
| 19 |  |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.9785 | 0.9516 | 0.9707 | 0.9611 | 28m 45s | 1725 | 0.9785 | GPU T4 x2 Kaggle
|  |  | V1 | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.9765 | 0.901 | 0.9817 | 0.9396 | 7m 7s | 427 | 0.9765 | GPU T4 x2 Kaggle |  |  |  | Cara save model di Kaggle? | done
|  |  | V3 | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.975 | 0.9352 | 0.9762 | 0.9553 | 21m 59s | 1319 | 0.975 | GPU T4 x2 Kaggle | Awalnya Error, ternyata harus diubah transformnya, karena Model Inception V3 mengharapkan gambar input berukuran minimal 299 x 299 piksel, lalu pada bagian def train_model juga mengganti outputs = outputs.squeeze(), karena menghasilkan: AttributeError: 'InceptionOutputs' object has no attribute 'squeeze'. Dengan penanganan output dari model Inception v3 pada saat pelatihan (phase == 'train'), sehingga mengambil output logit utama dengan outputs.logits karena model Inception v3 mengembalikan tuple yang terdiri dari (main output, auxiliary output). Pada saat evaluasi, hanya menggunakan output utama. |  |  | Cara load model di Kaggle? | done
Pekerja | Model (pretrained = No) |  |  | Epoch | Learning rate | Optimizer | Criterion
[8 empty] | Test (best model) (terhadap 1.00) |  |  |  | Waktu Training | Waktu Training (s) | Best Test Acc | Machine
| VGG | ResNet | GoogleNet |  |  |  |  | Accuracy | Precision | Recall | F1-Score
Calvin |  | ResNet18 |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.9535 | 0.9083 | 0.9232 | 0.9157 | 6m 14s | 374 | 0.9535 | GPU T4 x2 Kaggle
|  | ResNet34 |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.9465 | 0.8793 | 0.9324 | 0.9051 | 9m 9s | 549 | 0.9465 | GPU T4 x2 Kaggle
|  | ResNet50 |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.9125 | 0.7915 | 0.9232 | 0.8523 | 15m 12s | 912 | 0.9125 | GPU T4 x2 Kaggle
|  | ResNet101 |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.8805 | 0.7619 | 0.819 | 0.7894 | 26m 2s | 1562 | 0.8805 | GPU T4 x2 Kaggle
| 11 |  |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.952 | 0.902 | 0.925 | 0.9134 | 15m 51s | 951 | 0.952 | GPU T4 x2 Kaggle
| 13 |  |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.951 | 0.906 | 0.9159 | 0.9109 | 22m 34s | 1354 | 0.951 | GPU T4 x2 Kaggle | skip download pth VGG.. 1.5 GB perfile
| 16 |  |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.95 | 0.9013 | 0.9177 | 0.9094 | 27m 1s | 1621 | 0.95 | GPU T4 x2 Kaggle
| 19 |  |  | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.939 | 0.8583 | 0.9305 | 0.893 | 31m 8s | 1868 | 0.939 | GPU T4 x2 Kaggle
|  |  | v1 | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.9525 | 0.9201 | 0.9049 | 0.9124 | 7m 0s | 420 | 0.9525 | GPU T4 x2 Kaggle
|  |  | v3 | 25 | 0.0001 | adam | BCEWithLogitsLoss | 0.8905 | 0.7971 | 0.8044 | 0.8007 | 21m 48s | 1308 | 0.8905 | GPU T4 x2 Kaggle |  | grafik buat excel sj
Pekerja | Model (pretrained = No); criterion : CrossEntropyLoss |  |  | Epoch | Learning rate | Optimizer | Criterion
[8 empty] | Test (best model) (terhadap 1.00) |  |  |  | Waktu Training | Waktu Training (s) | Best Test Acc | Machine
| VGG | ResNet | GoogleNet |  |  |  |  | Accuracy | Precision | Recall | F1-Score
Satrio |  | 18 |  | 25 | 0.0001 | adam | CrossEntropyLoss | 0.932 | 0.937 | 0.9215 | 0.924 | 6m 3s | 363 | 0.932 | GPU T4 x2 Kaggle | 360 | 3 | 363
|  | 34 |  | 25 | 0.0001 | adam | CrossEntropyLoss | 0.9222 | 0.917 | 0.902 | 0.905 | 8m 44s | 524 | 0.9222 | GPU T4 x2 Kaggle | 480 | 44 | 524
|  | 50 |  | 25 | 0.0001 | adam | CrossEntropyLoss | 0.8965 | 0.9106 | 0.8965 | 0.8996 | 15m 9s | 909 | 0.8965 | GPU T4 x2 Kaggle | 900 | 9 | 909
|  | 101 |  | 25 | 0.0001 | adam | CrossEntropyLoss | 0.866 | 0.8605 | 0.864 | 0.8609 | 24m 55s | 1495 | 0.866 | GPU T4 x2 Kaggle | 1440 | 55 | 1495
| 11 |  |  | 25 | 0.0001 | adam | CrossEntropyLoss | 0.9355 | 0.8172 | 0.762 | 0.6877 | 15m 4s | 904 | 0.9355 | GPU T4 x2 Kaggle | 900 | 4 | 904
| 13 |  |  | 25 | 0.0001 | adam | CrossEntropyLoss | 0.896 | 0.9004 | 0.896 | 0.8897 | 21m 55s | 1315 | 0.896 | GPU T4 x2 Kaggle | 1260 | 55 | 1315
| 16 |  |  | 25 | 0.0001 | adam | CrossEntropyLoss | 0.946 | 0.9456 | 0.946 | 0.9455 | 24m 45s | 1485 | 0.946 | GPU T4 x2 Kaggle | 1440 | 45 | 1485
| 19 |  |  | 25 | 0.0001 | adam | CrossEntropyLoss | 0.926 | 0.9812 | 0.917 | 0.9139 | 29m 14s | 1754 | 0.926 | GPU T4 x2 Kaggle | 1740 | 14 | 1754
|  |  | v1 | 25 | 0.0001 | adam | CrossEntropyLoss | 0.9535 | 0.9262 | 0.9005 | 0.9044 | 6m 49s | 409 | 0.9535 | GPU T4 x2 Kaggle | 360 | 49 | 409
|  |  | v3 | 25 | 0.0001 | adam | CrossEntropyLoss | 0.852 | 0.8807 | 0.822 | 0.8311 | 21m 27s | 1287 | 0.852 | GPU T4 x2 Kaggle | 1260 | 27 | 1287

## Validation
ResNet-50 | 1 | 2 | 3 | 4 | 5 | ResNet-18 | 1 | 2 | 3 | 4 | 5
Female | 0 | 0 | 0 | 0 | 0 | Female | 0 | 1 | 0 | 1 | 1
Male | 0 | 0 | 1 | 1 | 1 | Male | 1 | 1 | 1 | 1 | 1
Inference time (ms/image) | 140.2539 |  |  |  |  | Inference time (ms/image) | 115.6472
VGG-19 | 1 | 2 | 3 | 4 | 5
Female | 0 | 0 | 0 | 0 | 0
Male | 1 | 1 | 1 | 1 | 1
Inference time (ms/image) | 103.7431
Inception V1 | 1 | 2 | 3 | 4 | 5 | Inception V3 | 1 | 2 | 3 | 4 | 5
Female | 1 | 1 | 1 | 1 | 1 | Female | 1 | 1 | 1 | 0 | 0
Male | 1 | 1 | 1 | 1 | 1 | Male | 1 | 0 | 0 | 1 | 1
Inference time (ms/image) | 70.7185 |  |  |  |  | Inference time (ms/image) | 135.5324
Without Pretrain
ResNet-18 | 1 | 2 | 3 | 4 | 5
Female | 0 | 0 | 0 | 0 | 0
Male | 1 | 1 | 1 | 1 | 1
Inference time (ms/image) | 53.7727
VGG-11 | 1 | 2 | 3 | 4 | 5
Female | 0 | 0 | 0 | 0 | 0
Male | 1 | 1 | 1 | 1 | 1
Inference time (ms/image) | 19.0841
Inception V1 | 1 | 2 | 3 | 4 | 5
Female | 0 | 0 | 0 | 0 | 0
Male | 1 | 1 | 1 | 1 | 1
Inference time (ms/image) | 39.8222